## Slide 1: SOFTWARE PROJECT MANAGEMENT AND COST ESTIMATION

## Slide 2: Object points
Function related metric developed for 4G languages
What is a 4GL
4GL focus on the task to be achieved rather than the process involved, example
  SQL
  Powerbuilder

## Slide 3: Object points (function + code)
Count number of
  screens
  reports
  3GL components (Java, C++ classes)
For each use following weighting based on complexity
Object type simple Media Difficult
Screen 1 2 3
Report 2 5 8
3GL components 10

## Slide 4: Function points verses Object points
Function points
  Established standard
  Much legacy estimation data available
  Supported by many tools
  Can be calculated very early on, requirements stage
Object points
  Newer
  Easier to calculate
  Provides allowance for re-use

## Slide 5: Cost Estimation
From size estimation (FP, OP or KLOC)
Map to cost using cost estimation model
Two error factors
  Original estimation error
  Cost derivation error
Or
Use direct estimation
  E.g. poker planning

## Slide 6: Factors affecting productivity
Application domain experience
Process quality
Project size
Technology support
Working environment
Notes: Individuals in a project may vary in their productivity by a factor of 10 (Boehm, et al. 1995), that is from 4 object points per month to 50.
The composition of the team and other factors must be taken into consideration in the overall estimate being made.
These other factors are:
Knowledge of the application domain
The software process used in development – if these are good productivity is higher (we return to this later)
Large projects need communication with less time for development and high productivity
Good CASE tools, configuration management system etc improve productivity
Quietness and private areas contribute to better productivity

## Slide 7: Estimation techniques
Algorithmic cost modelling e.g. Constructive Cost Modelling (CoCoMo)
Expert judgement
Estimation by analogy
Parkinson’s Law
Pricing to win
Notes: Using historical cost information an equation is developed that relates some software metric (usually size) to cost. Estimates of the metric then predict the cost/effort required.
Multiple experts estimate, then discuss and agree a compromise cost.
The cost of new project is estimated by analogy with comparable completed projects.
Parkinson’s Law: work expands to fill the time. If there are 5 people and the software must be delivered in 6 months then the effort estimate is 30 person months.
The customers budget determines the cost. Makes sense if the system can be shipped to a subsequent customer.
However, most methods assume that will be no significant changes in the way software development is done. Changes in the past 10 years have shown that this is not a safe assumption. Examples of changes that affect estimation include:
Distributed and grid based systems
Web facilities
Entity Resource Planning or db centred systems
Shrink wrapped software
Module reuse
Scripting facilities
CASE tools

## Slide 8: Constructive Cost Modelling (CoCoMo)
Notes: Constructive Cost Modelling (COCOMO) is an algorithmic model that is well known, widely used as a commercial tool, and software for it is in the public domain.
It was first proposed by Boehm, B. in his 1981 book “Software engineering economics”, Prentice-Hall. The definitive book for the method is Boehm, B. (2000) “Software Cost Estimation with COCOMO II”, Prentice-Hall.
Summary of the COCOMO II method is in the paper Boehm, B., Clark, B. et al. (1995) “Cost models for future software life cycle processes: COCOMO II”, Annals of Software Engineering, Vol 1, p57-94.
COCOMO assumes a stable software house or software department for which historical measures of software productivity exist. Where this is not available, the published data from finished software projects may be used.
In 1981 COCOMO was based on the waterfall model using a programming language. Now, it can cope with changes in method (e.g. the spiral or incremental model etc), use of shrink wrapped components such as Oracle that provides both a DBMS and full database programming language, and the use of various CASE tools and hardware.

## Slide 9: Algorithmic cost modelling
Assumes there is mathematical relationship between
  Measure of size of project and how much effort it takes
  Uses data from many projects to produce model
  Tries to take into account variations in input factors

## Slide 10: Algorithmic cost modelling research
Take a series of projects
Make estimations at begin and part way through
  Total size
  Complexity
  Re-use factors
Measure how long the project takes in person months
Try and correlate these 2 taking into account both factors

## Slide 11: Problems with algorithmic cost modelling
Development approach change
Estimation of project size and complexity is difficult
Model cannot take into account all factors
  Development and testing approach
  Regressive development way overrun time

## Slide 12: COCOMO
Barry W. Boehm 1981
63 projects at TRW Aerospace
From 2,000 to 100,000 lines
COCOMO II 2000
  University of Southern California
  University of California Irvine
  COCOMO™ II Affiliates' Program

## Slide 13: Modelling ..
Effort
Staff
months
Size of project (normalized for complexity etc)
Outlier?
Find out why?

## Slide 14: Modelling Cocomo
Try and find mathematical relationship which fits graph on previous page
Some thing like S^C
Where S is size of project and C is dependent on type of project
S may be increased dependent on complexity (see function points etc)

## Slide 15: The COCOMO method
Input
  Conduct of the project (e.g. design model)
  Staff available
  Hardware and CASE tools involved
  Nature of the product
Output estimates
  Size of the system (LOC and function points)
  Project schedules and team factors
  Cost and staffing profiles.

## Slide 16: Summary
Cost Estimation Modelling
  Relies on expert judgement
  Requires much effort
  Produces subject results
Alternatives
  Group estimation
  Analogy estimation
  Pricing to win